## Status Report Day 1
Status Report for Team #
Project |  | Status: (Red/Yellow/Green)
Date: | 2026-10-05 | Overall Status: | Green
Contact: | Selina | Explanation: | good progress so far
Prepared By: | Team 4
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Anatasiia | completed entity relationship diagram, DB schema.sql, data.sql with initial currency data, set up the MySQL database and verified the schema and seed data
Krish | done front end login page and made progress on conversion page
Selina | completed flow chart
ID # | Key Issues | Action Plan |  |  | Status
None
Critical Milestones |  | Health | Due Date | Comment/Status %
User login |  | Green | 2026-10-05 | 70%
Currency converter with swap currency feature |  | Green | 2026-10-06
Save converted to history feature with option to add note |  | Green | 2026-10-06
Watchlist with add, edit, remove, select feature |  | Green | 2026-10-07
Conversion History with delete feature |  | Green | 2026-10-07
Currency information |  | Green | 2026-10-06
Presentation |  | Green | 2026-10-08
Thursday dry run |  | Green | 2026-10-08
Green
Green

## Status Report Day 2
Status Report for Team #4
Project |  | Status: (Red/Yellow/Green)
Date: | 2026-10-06 | Overall Status: | Green
Contact: | teams | Explanation: | good progress so far
Prepared By: | Anastasiia
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Anatasiia | created models for currency, history, user and watchlist, implemented RowMappers
Krish | finished working on login/sign up page, loading data from the database into the currency converter
Selina | implemented conversion history service and controller, currency service and controller
ID # | Key Issues | Action Plan |  |  | Status
None
Critical Milestones |  | Health | Due Date | Comment/Status %
User login |  | Green | 2026-10-05 | 100%
Currency converter with swap currency feature |  | Green | 2026-10-06 | 70%
Save converted to history feature with option to add note |  | Green | 2026-10-06 | 70%
Watchlist with add, edit, remove, select feature |  | Green | 2026-10-07 | 15%
Conversion History with delete feature |  | Green | 2026-10-07 | 50%
Currency information |  | Green | 2026-10-06 | 85%
Presentation |  | Green | 2026-10-08
Thursday dry run |  | Green | 2026-10-08
Green
Green

## Status Report Day 3
Status Report for Team #4
Project |  | Status: (Red/Yellow/Green)
Date: | 2026-10-07 | Overall Status: | Green
Contact: | email | Explanation: | Nearly done will all core features
Prepared By: | Krish
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Anatasiia | created dao for currency, user, conversion history and watchlist, finishing work on dao implementations
Krish | create the currency information page, ensure api works and converts currencies and also add functionality to favourite pairs
Selina | created controller and service layer for favourites, added live currency conversion with unirate api
ID # | Key Issues | Action Plan |  |  | Status
None
Critical Milestones |  | Health | Due Date | Comment/Status %
User login |  | Green | 2026-10-05 | 100%
User Creation |  | Green | 2026-10-06 | 100%
Currency converter with swap currency feature |  | Green | 2026-10-06 | 100%
Save converted to history feature with option to add note (note is not yet done) (optional) |  | Green | 2026-10-06 | 70%
Watchlist with add, edit, remove, select feature |  | Green | 2026-10-07 | 100%
Conversion History with delete feature |  | Green | 2026-10-07 | 40%
Currency information |  | Green | 2026-10-06 | 100%
Presentation |  | Green | 2026-10-08 | 40%
Thursday dry run |  | Green | 2026-10-08
Frontend UI make nicer if time remains |  | Green
Green

## Status Report Day 4
Status Report for Team #4
Project |  | Status: (Red/Yellow/Green)
Date: | 2026-10-08 | Overall Status: | Green
Contact: | email | Explanation: | Done with all core features
Prepared By: | Selina
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Anatasiia | Complete frontend impl for some of the pages + presentation
Krish | presentation and fixed user creation bug
Selina | Complete frontend impl for some of the pages + presentation
ID # | Key Issues | Action Plan |  |  | Status
None
Critical Milestones |  | Health | Due Date | Comment/Status %
User login |  | Green | 2026-10-05 | 100%
User Creation |  | Green | 2026-10-06 | 100%
Currency converter with swap currency feature |  | Green | 2026-10-06 | 100%
Save converted to history feature with option to add note (note is not yet done) (optional) |  | Green | 2026-10-06 | 100%
Watchlist with add, edit, remove, select feature |  | Green | 2026-10-07 | 100%
Conversion History with delete feature |  | Green | 2026-10-07 | 100%
Currency information |  | Green | 2026-10-06 | 100%
Presentation |  | Green | 2026-10-08 | 100%
Thursday dry run |  | Green | 2026-10-08 | 100%
Frontend UI make nicer if time remains (will be done by end of today) |  | Green | 2026-10-08 | 90%
Green